## Sheet1
|  | Davach Holdings |  | Ready to Start?
4 Plex Property Schedule
Project Stages | Task ID | Task | Trigger Task ID(s) To Start Task | To Do List | Completed (Yes / No) | Task Owner Internal Person | Vendor If Applicable | Typical Task Timeline From Start | Task Owner Start Date | Finish Date | Total Actual Days For Task | Vendor | Cost | Invoice Number | Payment Method | Storage Location | Template Document
Pre Development | DE00 | Demolition Permit
| DE01 | Demolition Permit Submission | P10 | Waiting | no |  |  | 1.00
| DE02 | Pay Demolition Permit Fees | DE01 | Waiting | no |  |  | 1.00
| DE03 | Water Disconnect | P10 | Waiting | no |  |  | 30.00
| DE04 | Gas Disconnect | DE03 | Waiting | no |  |  | 15.00
| DE05 | Power Disconnect | P10 | Waiting | no |  |  | 20.00
| DE06 | Asbestoes Testing | P08 | Waiting | no |  |  | 1.00
| DE07 | Asbestoes Abatement (If Applicable) | DE06 | Waiting | no |  |  | 5.00
| DE08 | Clearance Letter | DE07 | Waiting | no |  |  | 1.00
| DE09 | Submit Clearance Letter and Confirmation of Disconnects | DE03, DE04, DE05, DE08 | Waiting | no |  |  | 1.00
| DE10 | Notice Application Is Complete | DE09 | Waiting | no |  |  | 1.00
| DE11 | Demolition Development Permit Issued | DE10 | Waiting | no |  |  | 3.00
| DE12 | Post Demolition Sign | DE11 | Waiting |  |  |  | 5.00
| DE13 | Demolition Building Permit Issued | DE12 | Waiting | no |  |  | 1.00
| DE14 | Demolition | DE13 | Waiting | no |  |  | 3.00
| DP00 | Development Permit
| DP01 | Development Permit Submission | DP03, DP04, DP05, DP06, DP07,DP08 | Waiting | no |  |  | 1.00
| DP02 | Pay Development Permit Fees | DP01 | Waiting | no |  |  | 1.00
| DP03 | RDP | P07 |  |  |  |  | 3.00
| DP04 | Architectual Drawings | P07 | Waiting | no |  |  | 15.00
| DP05 | Landscaping | DP08 | Waiting | no |  |  | 3.00
| DP06 | Plot Plan | DP04 | Waiting | no |  |  | 3.00
| DP07 | Grading Plan | DP08 | Waiting | no |  |  | 3.00
| DP08 | Civil Engineering | DP05 | Waiting | no |  |  | 5.00
| DP09 | Submit New Service APP Epcor | DP07, DP06 | Waiting | no |  |  | 1.00
| DP10 | IWASS Approval | DP08 | Waiting | no |  |  | 40.00
| DP11 | Development Permit Issued | DP09, DP01, DP02 | Waiting | no |  |  | 60.00
| BP00 | Buidling Permit
| BP01 | Building Permit Submission | BP03, BP05, BP06, BP07, BP08 | Waiting | no |  |  | 1.00
| BP02 | Pay Building Permit Fees | BP01 | Waiting | no |  |  | 1.00
| BP03 | Structual Engineering | DP11 | Waiting | no |  |  | 5.00
| BP04 | IFPA Approval | BP01 | Waiting | no |  |  | 3.00
| BP05 | Floor Joist / Roof Truss Layout / Stamped | BP03 | Waiting | no |  |  | 10.00
| BP06 | Home Warranty Exemption | DP11 | Waiting | no |  |  | 30.00
| BP07 | Energy Report | DP11 | Waiting | no |  |  | 10.00
| BP08 | Window Schedule | DP11 | Waiting | no |  |  | 3.00
| BP09 | Energy Report | DP11 | Waiting | no |  |  | 10.00
| BP10 | Footing & Foundation Permit (If Applicable) | BP01 | Waiting | no |  |  | 1.00
| BP11 | Building Permit Issued | BP04, BP01, BP02 | Waiting | no |  |  | 30.00
Acquisition | P00 | Purchase
| P01 | Find Lot |  | N/A | no |  |  | 1.00 | 2026-03-09 |  | 56
| P02 | Check Lot Dimesions With Architect | P01 | Waiting | no |  |  | 1.00
| P03 | Check Title With Realtor | P01 | Waiting | no |  |  | 1.00
| P04 | Confirm NO RC | P03 | Waiting | no |  |  | 1.00
| P05 | Submit Offer | P02, P03, P04 | Waiting | no |  |  | 1.00
| P06 | Provide Depoist | P05 | Waiting | no |  |  | 1.00
| P07 | Due Diligence | P06 | Waiting | no |  |  | 5.00
| P08 | Waive Conditions | P07 | Waiting | no |  |  | 1.00
| P09 | Time Till Closing | P08 | Waiting | no |  |  | 180.00
| P10 | Close on Property | LC06 | Waiting | no |  |  | 1.00
| LC00 | Land Closing
| LC01 | Secure Lender (If Applicable) | P07 | Waiting | no |  |  | 30.00
| LC02 | Land Apprasial | P07 | Waiting | no |  |  | 15.00
| LC03 | Cash Short Fall | LC01, LC02 | Waiting | no |  |  | 1.00
| LC04 | Secure Short Fall | P09 | Waiting | no |  |  | 1.00
| LC05 | Insurance | P09 | Waiting | no |  |  | 3.00
| LC06 | Provide Cash Short Fall Week Prior To Closing | P09 | Waiting | no |  |  | 1.00
Financing | CF00 | Construction Financing
| CF01 | CMHC Or Conventional | P08 | Waiting | no |  |  | 90.00
| CF02 | Final Build Apprasial | DP03 | Waiting | no |  |  | 21.00
| CF03 | Apprasial Reliance Letter | CF02 | Waiting | no |  |  | 3.00
| CF04 | ESA | CF08 | Waiting | no |  |  | 15.00
| CF05 | ESA Reliance Letter | CF04 | Waiting | no |  |  | 3.00
| CF06 | Detailed Construction Budget | DP03 | Waiting | no |  |  | 3.00
| CF07 | COI (If Applicable) | CF08 | Waiting | no |  |  | 60.00
| CF08 | Signed Term Sheet | CF01 | Waiting | no |  |  | 30.00
| CF09 | Complete Due Diligence Package | CF08 | Waiting | no |  |  | 30.00
| CF10 | Commitment Letter | CF09 | Waiting | no |  |  | 45.00
| CF11 | Insurance | CF10 | Waiting | no |  |  | 3.00
| CF12 | Legal | CF10 | Waiting | no |  |  | 3.00
| CF13 | Agree on QS | CF08 | Waiting | no |  |  | 1.00
| CF14 | Budget Review Submission | CF10 | Waiting | no |  |  | 15.00
| CF15 | Draw Request | CF14 | Waiting | no |  |  | 10.00
| QS00 | QS
| QS01 | Complete QS Needed Document Package | P08 | Waiting | no |  |  | 15.00
| QS02 | Budget Review | QS01 | Waiting | no |  |  | 15.00
| QS03 | First Draw Request | QS01, CF12, INS01, INS02, C05 | Waiting | no |  |  | 10.00
| QS04 | Second Draw Request | INS03, C06, C07, C08, C09, C16 | Ready | no |  |  | 5.00
| QS05 | Third Draw Request | C20 | Waiting | no |  |  | 5.00
| QS06 | Fourth Draw Request | C27 | Waiting | no |  |  | 5.00
| QS07 | Final Draw Request | C29 | Waiting | no |  |  | 10.00
| TO00 | Take Out Financing
| TO01 | Signed Term Sheet | QS03 | Waiting | no |  |  | 15.00
| TO02 | Complete Due Diligence Package | TO01 | Waiting | no |  |  | 15.00
| TO03 | Secure COI | TO02 | Waiting | no |  |  | 30.00
| TO04 | Rate Lock | QS07 | Waiting | no |  |  | 1.00
| TO05 | Commitment Letter | TO03, TO01 | Waiting | no |  |  | 20.00
| TO06 | Insurance | TO05 | Waiting | no |  |  | 3.00
| TO07 | Legal | TO05 | Waiting | no |  |  | 3.00
Construction | C00 | Construction
| C01 | Stakeout | DE13 | Waiting | no |  |  | 3.00
| C02 | Excavation | C01 | Waiting | no |  |  | 3.00
| C03 | Footings | C02 | Waiting | no |  |  | 3.00
| C04 | Cribbing | C03 | Waiting | no |  |  | 4.00
| C05 | Services / Backfill | C02, C03 | Waiting | no |  |  | 3.00
| C06 | Framing | C05 | Waiting | no |  |  | 20.00
| C07 | Window Installation | C06 | Waiting | no |  |  | 2.00
| C08 | Door Installation | C06 | Waiting | no |  |  | 1.00
| C09 | Lock Installation | C06 | Waiting | no |  |  | 1.00
| C10 | Ground Works | C06 | Waiting | no |  |  | 3.00
| C11 | Plumbing Stacks | C06 | Waiting | no |  |  | 10.00
| C12 | Hvac Stacks | C11 | Waiting | no |  |  | 10.00
| C13 | Electrical Rough ins | C12 | Waiting | no |  |  | 10.00
| C14 | Basement Concrete | C10, INS01 | Waiting | no |  |  | 3.00
| C15 | Basement Framing | C14 | Waiting | no |  |  | 5.00
| C16 | Roof | C06 | Waiting | no |  |  | 3.00
| C17 | Stucco | C16 | Waiting | no |  |  | 20.00
| C18 | Masonary | C17 | Waiting | no |  |  | 3.00
| C19 | Sidng and Eaves | C18 | Waiting | no |  |  | 20.00
| C20 | Insulation/Drywall | INS03 | Waiting | no |  |  | 30.00
| C21 | Prime | C20 | Waiting | no |  |  | 10.00
| C22 | Finishing Stage 1 | C21 | Waiting | no |  |  | 10.00
| C23 | Cabinents/Counters | C22 | Waiting | no |  |  | 5.00
| C24 | Paint | C23 | Waiting | no |  |  | 10.00
| C25 | Flooring | C24 | Waiting | no |  |  | 10.00
| C26 | Final Plumbing | C23 | Waiting | no |  |  | 5.00
| C27 | Finishing Stage 2 | C22, C24, C25 | Waiting | no |  |  | 10.00
| C28 | Notice of Substantial Completion | C27 | Waiting | no |  |  | 1.00
| C29 | Final Paint | C27 | Waiting | no |  |  | 5.00
| C30 | Hvac Final | C29 | Waiting | no |  |  | 2.00
| C31 | Electrical Final | C30 | Waiting | no |  |  | 2.00
| C32 | Flatwork | C05 | Waiting | no |  |  | 15.00
| C33 | Landscaping | C32 | Waiting | no |  |  | 15.00
| INS00 | Inspection
| INS01 | Plumbing Ground Work | C10 | Waiting | no |  |  | 20.00
| INS02 | Footing & Foundation | C03, C04 | Waiting | no |  |  | 10.00
| INS03 | Framing First Inspection | C06 | Waiting | no |  |  | 5.00
| INS04 | Insulation & Vapour Barrier | C20 | Waiting | no |  |  | 5.00
| INS05 | Natural Gas | C11 | Waiting | no |  |  | 5.00
| INS06 | Plumbing Stacks | C11 | Waiting | no |  |  | 5.00
| INS07 | Electrical Wiring Rough-in | C13 | Waiting | no |  |  | 5.00
| INS08 | HVAC Stack | C12 | Waiting | no |  |  | 5.00
| INS09 | HVAC Concealed Duct | C12 | Waiting | no |  |  | 5.00
| INS10 | Plumbing Rough-in Basement / Suite | C15 | Waiting | no |  |  | 5.00
| INS11 | Temporary Gas Heat |  | N/A | no |  |  | 5.00
| INS12 | Electrical Wiring Final | C31 | Waiting | no |  |  | 5.00
| INS13 | Final/Residential HVAC | C30 | Waiting | no |  |  | 5.00
| INS14 | Final Building | INS12, INS13 | Waiting | no |  |  | 5.00
| Q00 | Quotes
| Q01 | Lumber Package | DP10 | Waiting | no |  |  | 5.00
| Q02 | Window Package | DP10 | Waiting | no |  |  | 5.00
| Q03 | Excavation | BP01 | Waiting | no |  |  | 5.00
| Q04 | Footing / Foundation | BP01 | Waiting | no |  |  | 5.00
| Q05 | Framing | BP01 | Waiting | no |  |  | 5.00
| Q06 | Plumbing | BP01 | Waiting | no |  |  | 5.00
| Q07 | HVAC | BP01 | Waiting | no |  |  | 5.00
| Q08 | Electrical | BP01 | Waiting | no |  |  | 5.00
| Q09 | Cabinents | BP01 | Waiting | no |  |  | 5.00
| Q10 | Flooring | BP01 | Waiting | no |  |  | 5.00
| Q11 | Drywall/Insulation | BP01 | Waiting | no |  |  | 5.00
| Q12 | Finishing | BP01 | Waiting | no |  |  | 5.00
| Q13 | Painting | BP01 | Waiting | no |  |  | 5.00
| Q14 | Stucco | BP01 | Waiting | no |  |  | 5.00
| Q15 | Masonary | BP01 | Waiting | no |  |  | 5.00
| Q16 | Siding & Eaves | BP01 | Waiting | no |  |  | 5.00
| Q17 | Flatwork | BP01 | Waiting | no |  |  | 5.00
| Q18 | Landscaping | BP01 | Waiting | no |  |  | 5.00
| Q19 | Misc | BP01 | Waiting | no |  |  | 5.00
Utilities | UT00 | Utilities
| UT01 | Select Utility Supplier | INS05 | Waiting | no |  |  | 1.00
| UT02 | Gas Hook up | INS05 | Waiting | no |  |  | 60.00
| UT03 | Water Hook up | UT02 | Waiting | no |  |  | 60.00
| UT04 | Power Hook up | INS12 | Waiting | no |  |  | 60.00
Formulas:
Total Actual Days For Task = IF(LOWER([Completed (Yes / No)])="yes", INT([Finish Date]-[Task Owner Start Date]), IF([Task Owner Start Date]<>"", INT(TODAY()-[Task Owner Start Date]), ""))
Total Actual Days For Task = IF(ISBLANK([Task Owner Start Date]), "", IF([Completed (Yes / No)]="yes", INT([Finish Date]-[Task Owner Start Date]), INT(TODAY()-[Task Owner Start Date])))